Supporting: MSFKB3001 Identify processes in kitchen and bathroom projects

# Section 2 Assignment: Project schedule

|  |  |  |  |
| --- | --- | --- | --- |
| **Name** |  | **Date** |  |

### Instructions

Develop a project schedule for a kitchen renovation project. Use the information shown on the Assignment 2 page of the website to get all the details you’ll need, including the trades, tasks involved and number of hours required. Day 1 of Week 1 is already done for you.

Add as many rows to this table as you need.

You may submit the assignment to your trainer either by:

* printing out a hard copy and posting it in the mail
* saving the file electronically and sending it as an email attachment.

**Project schedule**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Day** | **Tradesperson** | **Task** | | **Start** | **Finish** | **Hours** |
| **WEEK 1** | | | | | | |
| Monday | Carpenter | Prepare the work area, remove old kitchen cabinets and floor covering, remove wall and ceiling sheeting | 7.00 am | | 4.00 pm | 8 (plus  1 hr for breaks) |
| Electrician | Terminate power and look at scope of the job | 9.00 am | | 10.30 am | 1.5 |
| Plumber | Terminate water and look at scope of the job | 10.00 am | | 11.30 am | 1.5 |
| Tuesday |  |  |  | |  |  |
| Wednes-day |  |  |  | |  |  |
| Thursday |  |  |  | |  |  |
| Friday |  |  |  | |  |  |
| Saturday |  |  |  | |  |  |
| **WEEK 2** | | | | | | |
| Monday |  |  |  | |  |  |

Add more rows as required